## OVERVIEW
RESULT
MODULE | TOTAL | TO GO | PASS | FAIL
Masters | 19 | 0 | 19
Beat | 21 | 0 | 21
Product | 6 | 0 | 6
Mobile App | 16 | 0 | 16
Stock & Sale | 8 | 0 | 8
Target | 9 | 0 | 9
Purchase Requisition | 3 | 0 | 3
SUM | 82 | 0 | 82 | 0
FEEDBACK Points | 31
Change | 0
Service | 0
Defect | 0

## STI Feedback Sheet
S No. | Type | Reported Source | Desciption | Type | Priority | Cusomter Status | Type | Classification | Effort In Man Days | Status | OffShore Remarks | Offshore Status | Onsite Remarks | Bugzilla ID | TEMWE Confirmation (For CR) | TEMWE Confirmation (For CR)
1 | UAT Feedback | User registration: | 1. Required fields and upload files on user registration process are not defined as requested 2. If same User information is entered twice, then alert is required by system 3. Unique ID for each employee needed to be defined in additional field (for mapping user with different systems) | CR | 0 |  |  |  | 8 |  | 20170515 : This will be done on UI. Is this required for upload of user and org creation?? | Open | 20170511 : This will be for both user and org creation. We need to discuss with Romet to get complete detail. Verification document to be uploaded while onboarding users in both org/user creation. | Bug 1326 |  |  | In Development
2 | UAT Feedback | User registration: | Same User can’t be used for different/multiple Organization | [6 empty] | Waiting For Customer | User ID Is Unique in the S-NOC. 20170511 : Need to test and confirm on existing feature. | Open | 20170511 : Client expectation - from one organization user will be terminated and same will be created for another organization. It is like switching company.
3 | UAT Feedback | User registration: | Combined with 1st point | CR | 0 | [5 empty] | User ID Is Unique in the S-NOC. is this for creation of the user ? 20170511 : This will be given only for STIADMIN. | Open | 20170511 : Now system showing user name already exist. System should show more information which org and which position currently the user name is. Need to confirm with Romet what are all the unique field validation is required. Like Mobile Number/Email ID etc.(This will be given only for STIADMIN) | Bug 1326
4 | UAT Feedback | User registration: | Combined with 1st point | [6 empty] | Void | Not clear. Need details of required fields for each user Type is this is about addtional feilds required while creation of the user | Open | 20170511 : We have User Ref Code in user creation. This field should be unique on SNOC system. Validation on mapping with other system has to be defined by timwe(Romet). | Bug 1326
5 | UAT Feedback | User transmission: | One position can have multiple parents | [6 empty] | Closed | This is possible with linking . If any thing addtionaly expected ?. need more clarity 20170511 : Not Feasible - Muthu | Closed | 20170511 : Here point is raised against on position not against organization.
6 | UAT Feedback | Create organization: | Additional fields and upload when creating user/organization are not defined as requested. | CR |  |  |  |  | 4 |  | Not clear. Need details of required fields for each user Type is this is about addtional feilds required while creation of the user. | Open | 20170511 : Account number/Bank name/Branch please make it as non mandatory . STI should share complete fields set up and mandatory/non-mandatory fields. |  |  |  | Released
7 | UAT Feedback | Security: | One user can have one active session at once | CR |  |  |  |  | 6 |  | This is blocked in mobile application with Device lock for the user id. Not on the web application | Open | 20170511 : Only one login should allowed in Web also. |  |  |  | Released
8 | UAT Feedback | Security: | Approval process (adding new user, organization, stock movement etc.) in system needed to be defined by STI. | [7 empty] | For which process ? and how many levels or approvals ? who are actors in the approval ? is the approval is limited to approve/reject ? Need more information on the work flow need and which process flows ? | Open On STI | 20170511 : Workflow and other details will be discussed with Romet in detail.
9 | UAT Feedback | Configuration: | STI Admin can’t edit under Role Features already created Role information | [7 empty] | This is role features to enables ? 20170511 : Role name change will affect role feature logic and this is predefined/one time activity on installation of system. NOt Feasible - Muthu | Closed | 20170511 : After enabling the Role Feature also it is not working.
10 | UAT Feedback | Configuration: | ‘Role Features’ list should be shorter (define role category and features), at the moment its setup based on Position. | [7 empty] | Not clear. What is meant by shorter ? | Open On STI | 20170511 : This will be completed by Romet and STI(Arief) Explanation : Channel admin , sale admin , B2C Sale, B2B sale likewise they will define roles and attache position with the same.
11 | UAT Feedback | Configuration: | STI-admin can’t add ‘Organization Type’ | [7 empty] | This is backend . Please share the information to configure by the Deployment team. | Closed | 20170511 : This is backend activity and not feasible from UI.
12 | UAT Feedback | Beat: | Beat has to be configured for Area wise not only for MITRA or any specific org | [7 empty] | understand at some level but need more clarity how the beat would be configured by areawise ? Location information already shown in the beat creation while selecting the pos list. 20170511 : Need to discuss with Amjath sir. | Open | 20170511 : Beat creation areawise. Like sale guy will travel and do tertiary sale to customer on specific location(Central Jakarta). The sale should not happen apart from tat area. Please confirm
13 | UAT Feedback | Beat: | Beat needs to create for sales guy on hourly basis | [7 empty] | This can be achived with mutiple beats for the FSE. 20170511 : Need to discuss with Amjath sir. | Open | 20170511 : What is multiple beat. Only one beat plan can be created per day. Requirement is, per day Sales Manger will create beat and assign to the sales guy it can be time basis.
14 | UAT Feedback | Target: | Target Hierarchy setting need to be defined by STI | [7 empty] | This is STI action item | Open On STI | 20170511 : Romet will get back on this.
15 | UAT Feedback | Overall: | Batch/upload creation (e.g. users, organization, products) | CR |  |  |  |  | 22 |  | Products : Yes. This feature is already availble ORG : Yes. This feature is already availble Users: No. This need a customization | Open | 20170511 : Yes aggreed. and stil user careation upload is not available in system . So point not closed.
16 | UAT Feedback | Overall: | If position is linked with another org position report will be displayed from source linked Area | [7 empty] | Not clear. Need more clarity on the requirement | Closed | 20170511 : On linking source area should get reflected for the Partner node. This is not feasible.
17 | UAT Feedback | Overall: | Product management is not working as requested: Device vs Plan vs Payment Method | CR | 0 | [5 empty] | Not clear. Need more clarity on the requirement | Open On STI | 20170511 : This is STI action point. Romet needs define with STI. | Bug 1327
18 | UAT Feedback | Overall: | One inventory has to be used for all sales users- specific Organization | CR |  |  |  |  | 6 |  | distributor have separate inventory they can do stock transfer to FSE they can perform the sale. 20170511 : This can be acheived only in Tertiary Sale. | Open | 20170511 : Distributor no need to do stock transfer for all the time. If required sale guy(FSE) can able to do sale from distributor account. 14/06/17 : This will be online sale. Since we are allowing offline sale can not maintain inventory.
19 | UAT Feedback | Overall: | For all orders notification (system icon, email etc.) is mandatory for any entity | CR |  |  |  |  | 2 |  | What is system icon ? Which orders notification has to go ? To whom the approvals will go ? | Open | 20170511 : If stock transfer/ secondary sale done then the target node should get alert on the same (Like it can be notification icon near to login screen). For all orders.
20 | UAT Feedback | Overall: | Serial Number format should be defined for Primary and Additional serial numbers | CR | 0 |  |  |  | 13 |  | Not clear. Need more clarity on the requirement. Please add more information in BUGZILA | Open | 20170511 : It is already updated in Bugzila and shared via mail. Bug : 1315 client bugzila. Internal Id : 9365 |  |  |  | Released
21 | CEO/COO Discussiont Point | Overall: | Purchase Requisition Flow (Approval1, Approval2, Warehouse, Finance) need to be defined | [7 empty] | Not clear. Need more clarity on the requirement | Open On STI | 20170511 : Need to confirm with Romet on commercially and this flow will be defined by STI with interface details
22 | CEO/COO Discussiont Point | Interface: | Integration with BSS; HRIS; SMS/EMAIL; TELEMARKETING; INVENTORY, FINANCE is mandatory. | CR | [6 empty] | For whcih Process the integration is required? What are list of interaface activities with each system? This has to detailed in clear for the integration points | Open On STI | 20170511 : Required discussion with Romet to get information in detail. 20170614 : Not clear on integration requirement.
23 | Romet Email - Points |  | Attendance via Mobile APP is not working as requested (work start, clock-in, periodic check, clock out). Each parent node for the Sales Rep will send pic to take selfie and submit to the system. STIADMIN and parent node can able to see the photo identification. | CR | 0 | [5 empty] | Attendence module is customization part of Phase-2. This is not yet delivered as per the plan. | Open | 20170511 : No idea on which phase it is.Please share me the Phase details. Even if it is in Phase-2 please comercially confirm with Romet. 20170614 : Status updated in Bugzila. | Bug 1329
24 | CEO/COO Discussiont Point | Territory sale: | Sell-out is not working as requested. End user customer data is not captured, but this is mandatory. | CR |  |  |  |  | 10 |  | Need to confirm the release date from Deployment. | Open | 20170511 : While doing sell out customer name and mobile number and email ID has to be recorded. | Bug 1328 | Approved as CR - Delivery Intiation | Delivered on (31-May-2017) | Released
25 | CEO/COO Discussiont Point | Secondary sale: | While doing secondary sale automatic/upload stock entry is needed | CR |  |  |  |  | 17 |  | Is this is for csv upload the serial numbers while secondary sales on web application(only) ? | Open | 20170511 : For now this will be in web only. | Bug 1404
26 | CEO/COO Discussiont Point | Reporting: | Reporting data by STI BI-team needed to be defined by STI | [7 empty] | This is STI action item | Open On STI | 20170511 : Yes. Pending with Romet/STI
27 | UAT Feedback | Reporting: | Information in Dashboard needed to be defined by STI | [7 empty] | This is STI action item | Open On STI | 20170511 : Yes. Pending with Romet/STI
28 | UAT Feedback | Reporting: | Full visual overview (Tree view) of organization & sub-organization & users | [7 empty] | This is already available | Open | 20170511 : showing organization in coverage view based on Filtration. STI requested for full view in single screen or map or some hierarchy structure. By default show all organization on list.
29 | Romet Point | Documentation: | Need list description every Role features with description (part of FSD) | [7 empty] | This is already available and shared the FSD by Swamy | Open | 20170511 : FSD needs to be reviewd.
30 | UAT Feedback | Beat | is Beat can be created and assigned for linked organization node?.(STI main pertner organization type is called Agnecy Org. and these organizations are linked with STI sales users. These sales user want to create beat and assign to Agency org) | CR |  |  |  |  | 3 |  | 20170511 : This can be done through oranization selection on beat creation. only for Primary Org beat creation. | Open |  |  |  |  | Released
31 | Discussion point with Arief | Sale | Tertiary Sale report customer info with document and additional serial number details are required. (As confirmed by Arief given/shared four serial numbers will be available for all products if anything new then changes required in Tertiary sale report and in system) | CR |  |  |  |  | 15

## UAT Tescase List
Module | Usecase Case ID | Test Case ID | Test Case | Result | Remark | Tested By | Target Date
Masters | UC-MS-01 | TC-UC-MS-01-1 | Organization Template/Structure creation - Distributor Organization | Pass |  | Diamaz/Anjei/Arief | 2017-05-04
Masters | UC-MS-02 | TC-UC-MS-02-01 | Organization Template/Structure creation - POS(Retailer) Organization | Pass |  | Diamaz/Anjei/Arief | 2017-05-04
Masters | UC-MS-03 | TC-UC-MS-03-01 | Organization creation - Sales Organization | Pass |  | Diamaz/Anjei/Arief | 2017-05-04
Masters | UC-MS-04 | TC-UC-MS-04-01 | Organization creation - Distributor Organization | Pass |  | Diamaz/Anjei/Arief | 2017-05-04
Masters | UC-MS-05 | TC-UC-MS-05-01 | Organization creation - POS(Retailer) Organization | Pass |  | Diamaz/Anjei/Arief | 2017-05-04
Masters | UC-MS-06 | TC-UC-MS-06-01 | User Creation | Pass |  | Diamaz/Anjei/Arief | 2017-05-04
Masters | UC-MS-07 | TC-UC-MS-07-01 | Create Link between Distribution and POS(Reatiler) Organization | Pass |  | Diamaz/Anjei/Arief | 2017-05-04
Masters | UC-MS-08 | TC-UC-MS-08-01 | Master Data Creation - Organizational Unit Master | Pass |  | Diamaz/Anjei/Arief | 2017-05-04
Masters | UC-MS-08 | TC-UC-MS-08-02 | Master Data Creation -Generic Master | Pass |  | Diamaz/Anjei/Arief | 2017-05-04
Masters | UC-MS-09 | TC-UC-MS-09-01 | Role Features - Enable/Disable features by System Admin | Pass |  | Diamaz/Anjei/Arief | 2017-05-04
Masters | UC-MS-10 | TC-UC-MS-10-01 | Modify organization - Distributor Organization | Pass |  | Diamaz/Anjei/Arief | 2017-05-04
Masters | UC-MS-11 | TC-UC-MS-11-01 | User modification | Pass |  | Diamaz/Anjei/Arief | 2017-05-04
Masters | UC-MS-12 | TC-UC-MS-12-01 | Assign Transition - Default transition | Pass |  | Diamaz/Anjei/Arief | 2017-05-04
Masters | UC-MS-13 | TC-UC-MS-13-01 | Manage User- Unlocking the user | Pass |  | Diamaz/Anjei/Arief | 2017-05-04
Masters | UC-MS-13 | TC-UC-MS-13-02 | Manage User- UnBlocking the user | Pass |  | Diamaz/Anjei/Arief | 2017-05-04
Masters | UC-MS-14 | TC-UC-MS-14-01 | Manage User- Manage Password | Pass |  | Diamaz/Anjei/Arief | 2017-05-04
Masters | UC-MS-15 | TC-UC-MS-15-01 | Ticker Message creation | Pass |  | Diamaz/Anjei/Arief | 2017-05-04
Masters | UC-MS-15 | TC-UC-MS-15-02 | Ticker Message modification | Pass |  | Diamaz/Anjei/Arief | 2017-05-04
Masters | UC-MS-16 | TC-UC-MS-16-01 | Remove User from Node/Position | Pass |  | Diamaz/Anjei/Arief | 2017-05-04
Beat | UC-BT-01 | TC-UC-BT-01 -01 | Beat Creation for Sales Representative(FSE) and daily schedular and Mode by Frequncy | Pass |  | Diamaz/Anjei/Arief | 2017-05-04
Beat | UC-BT-01 | TC-UC-BT-01 -02 | Beat Creation for Sales Representative(FSE) and daily schedular and Mode By Day | Pass |  | Diamaz/Anjei/Arief | 2017-05-04
Beat | UC-BT-01 | TC-UC-BT-01 -03 | Beat Creation for Sales Representative(FSE) and weekly schedular and mode as "By Weekly" | Pass |  | Diamaz/Anjei/Arief | 2017-05-04
Beat | UC-BT-01 | TC-UC-BT-01 -04 | Beat Creation for Sales Representative(FSE) and Monthly schedular and mode as "By week number" | Pass |  | Diamaz/Anjei/Arief | 2017-05-04
Beat | UC-BT-01 | TC-UC-BT-01 -05 | Beat Creation for Sales Representative(FSE) and weekly schedular and mode as "By week number" | Pass |  | Diamaz/Anjei/Arief | 2017-05-04
Beat | UC-BT-01 | TC-UC-BT-01 -06 | Beat Creation for Sales Representative(FSE) and Monthly schedular and by date | Pass |  | Diamaz/Anjei/Arief | 2017-05-04
Beat | UC-BT-01 | TC-UC-BT-01 -07 | Beat Creation for Sales Representative(FSE) and Monthly schedular by date and by month | Pass |  | Diamaz/Anjei/Arief | 2017-05-04
Beat | UC-BT-01 | TC-UC-BT-01 -08 | Beat Creation for Sales Representative(FSE) and Monthly schedular and by day and frequency | Pass |  | Diamaz/Anjei/Arief | 2017-05-05
Beat | Uc-BT-01 | TC-UC-BT-01 -09 | Beat Creation for Sales Representative(FSE) and Yearly schedular | Pass |  | Diamaz/Anjei/Arief | 2017-05-05
Beat | UC-BT-02 | UC-BT-02-01 | Changing the status of the Beat | Pass |  | Diamaz/Anjei/Arief | 2017-05-04
Beat | UC-BT-03 | UC-BT-03 -01 | View the Beat Created | Pass |  | Diamaz/Anjei/Arief | 2017-05-04
Beat | UC-BT-03 | UC-BT-03 -01 | Edit the Beat Created | Pass |  | Diamaz/Anjei/Arief | 2017-05-05
Beat | UC-BT-04 | UC-BT-04 -01 | Beat DashBoard- Summary | Pass |  | Diamaz/Anjei/Arief | 2017-05-04
Beat | UC-BT-04 | UC-BT-04 -02 | Beat DashBoard- Map View | Pass |  | Diamaz/Anjei/Arief | 2017-05-04
Beat | UC-BT-04 | UC-BT-04 -03 | Beat DashBoard-Grid view | Pass |  | Diamaz/Anjei/Arief | 2017-05-04
Beat | UC-BT-05 | UC-BT-05-01 | Creation of the "Self Beat" | Pass
Beat | UC-BT-06 | UC-BT-06-01 | Changing the status of the Beat | Pass
Beat | UC-BT-07 | UC-BT-07-01 | Re-assigning the Beat to another Sales Representative(FSE) | Pass |  | Diamaz/Anjei/Arief | 2017-05-04
Beat | UC-BT-07 | UC-BT-07-01 | Reports of the Beat- Beat Plan Summary Report | Pass |  | Diamaz/Anjei/Arief | 2017-05-04
Beat | UC-BT-07 | UC-BT-07-04 | Reports of the Beat- "Outlets Visisting Frequency" | Pass |  | Dimaz | 2017-05-04
Beat | UC-BT-07 | UC-BT-07-05 | Reports of the Beat- "In - Out Report" | Pass |  | Diamaz/Anjei/Arief | 2017-05-04
Product | UC-PR-01 | TC-UC-PR-01-1 | Product Line Creation | Pass |  | Arief | 2017-05-04
Product | UC-PR-01 | TC-UC-PR-01-2 | Product Categories Creation | Pass |  | Arief | 2017-05-04
Product | UC-PR-01 | TC-UC-PR-01-3 | Product Sub Categories Creation | Pass |  | Arief | 2017-05-04
Product | UC-PR-02 | TC-UCSOPR-02-1 | Product Creation | Pass |  | Arief | 2017-05-04
Product | UC-PR-03 | TC-UCSOPR-03-1 | Product Modification | Pass |  | Arief | 2017-05-04
Product | UC-PR-03 | TC-UCSOPR-03-2 | Set Criteria to product | Pass |  | Arief | 2017-05-04
Mobile App | UC-MOB-01 | TC-UC-01-01 | Sync Menu – When the user logins into the application needs to sync first before performing the transactions | Pass |  | Diamaz/Anjei/Arief | 2017-05-04
Mobile App | UC-MOB-02 | TC-UC-MOB-02-01 | Secondary Sales to the unplanned POS(Retailer) | Pass |  | Diamaz/Anjei/Arief | 2017-05-05
Mobile App | UC-MOB-02 | TC-UC-MOB-02-02 | Capturing the Geo location of the unplanned POS(Retailer) | Pass |  | Diamaz/Anjei/Arief | 2017-05-04
Mobile App | UC-MOB-02 | TC-UC-MOB-02-03 | To View the Credit limit of the POS(Retailer) | Pass |  | Diamaz/Anjei/Arief | 2017-05-05
Mobile App | UC-MOB-02 | TC-UC-MOB-02-04 | To perform the Survey | Pass |  | Diamaz/Anjei/Arief | 2017-05-05
Mobile App | UC-MOB-02 | TC-UC-MOB-02-05 | To View the Survey | Pass |  | Diamaz/Anjei/Arief | 2017-05-05
Mobile App | UC-MOB-02 | TC-UC-MOB-02-06 | Capture POS(Retailer) Image of unplanned POS(Retailer) | Pass |  | Diamaz/Anjei/Arief | 2017-05-05
Mobile App | UC-MOB-03 | UC-MOB-03-01 | To Sales Representative(FSE) the Stock Adjustment | Pass |  | Diamaz/Anjei/Arief | 2017-05-05
Mobile App | UC-MOB-03 | TC-UC-MOB-03-02 | Viewing the Profile of Sales Representative(FSE) | Pass |  | Diamaz/Anjei/Arief | 2017-05-05
Mobile App | UC-MOB-04 | TC-UC-MOB-04-01 | Beat Plan- Secondary Sales | Pass |  | Diamaz/Anjei/Arief | 2017-05-05
Mobile App | UC-MOB-04 | TC-UC-MOB-04-02 | Beat Plan lat/long- Capture The geo locationPOS(Retailer) | Pass |  | Diamaz/Anjei/Arief | 2017-05-04
Mobile App | UC-MOB-04 | TC-UC-MOB-04-03 | Beat Plan - Capture POS(Retailer) Image | Pass |  | Diamaz/Anjei/Arief | 2017-05-04
Mobile App | UC-MOB-04 | TC-UC-MOB-04-04 | Beat Plan - Survey | Pass |  | Diamaz/Anjei/Arief | 2017-05-04
Mobile App | UC-MOB-06 | TC-UC-MOB-06-01 | Tertiary Sales – To sell the products directly to customers | Pass |  | Diamaz/Anjei/Arief | 2017-05-05
Mobile App | UC-MOB-11 | TC-UC-MOB-11-01 | Secondary Sales Price Guidance | Pass |  | Diamaz/Anjei/Arief | 2017-05-05
Mobile App | UC-MOB-12 | TC-UC-MOB-12-01 | Serial Number Search | Pass |  | Diamaz/Anjei/Arief | 2017-05-05
Stock & Sale | UC-SM-01 | TC-UC-SM-01-01 | Order Creation - Stock Entry | Pass |  | Diamaz/Anjei/Arief | 2017-05-04
Stock & Sale | UC-SM-02 | TC-UC-SM-02-01 | Order Creation - Stock Transfer | Pass |  | Diamaz/Anjei/Arief | 2017-05-04
Stock & Sale | UC-SM-03 | TC-UC-SM-03-01 | View Stock | Pass |  | Diamaz/Anjei/Arief | 2017-05-04
Stock & Sale | UC-SM-04 | TC-UC-SM-04-01 | Order Creation - Stock Return | Pass |  | Diamaz/Anjei/Arief | 2017-05-04
Stock & Sale | UC-SM-05 | TC-UC-SM-05-01 | Order Creation - Stock Adjustment | Pass |  | Diamaz/Anjei/Arief | 2017-05-04
Stock & Sale | UC-SM-07 | TC-UC-SM-07-01 | Order Creation - Direct Sale/ Secondary sale | Pass |  | Diamaz/Anjei/Arief | 2017-05-04
Stock & Sale | UC-SM-08 | TC-UC-SM-08-01 | Order Creation - Tertiary Sale | Pass |  | Diamaz/Anjei/Arief | 2017-05-04
Stock & Sale | UC-SM-09 | TC-UC-SM-09-01 | Order Creation - Sale Return | Pass |  | Diamaz/Anjei/Arief | 2017-05-04
Target | UC-TG-01 | TC-UC-TG-01 | Add metrics for Distribution hierarchy | Pass |  | Arief | 2017-05-05
Target | UC-TG-02 | TC-UC-TG-02 | Edit metrics for Distribution hierarchy | Pass |  | Arief | 2017-05-05
Target | UC-TG-03 | TC-UC-TG-03 | View target metrics for Distribution hierarchy | Pass |  | Arief | 2017-05-05
Target | UC-TG-04 | TC-UC-TG-04 | Revise formula for Distribution hierarchy | Pass |  | Arief | 2017-05-05
Target | UC-TG-04 | TC-UC-TG-05 | Edit formula for Distribution hierarchy | Pass |  | Arief | 2017-05-05
Target | UC-TG-06 | TC-UC-TG-06 | Set target for Distribution hierarchy | Pass |  | Arief | 2017-05-05
Target | UC-TG-07 | TC-UC-TG-07 | Modify target for Distribution hierarchy by parent node to his child node | Pass |  | Arief | 2017-05-05
Target | UC-TG-08 | TC-UC-TG-08 | View Target for Distribution hierarchy | Pass |  | Arief | 2017-05-05
Target | UC-TG-09 | TC-UC-TG-09 | View achievements for secondary Sale by performed by distributor | Pass |  | Arief | 2017-05-05
Purchase Requisition | UC-PR-01 | TC-UC-PR-01 | Distributor will raise purchase Requisition | Pass |  | Diamaz/Anjei/Arief | 2017-05-05
Purchase Requisition | UC-PR-02 | TC-UC-PR-02 | STI Sales user will approve and do secondary sale aginst PR | Pass |  | Diamaz/Anjei/Arief | 2017-05-05
Purchase Requisition | UC-PR-03 | TC-UC-PR-03 | Stock can be viewd in distributor account | Pass |  | Diamaz/Anjei/Arief | 2017-05-05

## Org, Hierarchy & Masters
SI.No | Use Case Id | Test Case SI.NO | Test Scenario | Prerequisite | Test Case | Expected Result | Actual Result | Test Case status | Comments
1 | UC-MS-01 | TC-UC-MS-01-1 | Organization Template/Structure creation - Distributor Organization | System/Sales Admin user should be already created and active. | 1.Login into SNOC application by SND Admin. 2.Select Administrator->Create User. | Distributor organization Template will be created with Distributor and required Representative's position nodes.
2 | UC-MS-02 | TC-UC-MS-02-01 | Organization Template/Structure creation - POS(Retailer) Organization | System/Sales Admin user should be already created and active. | 1.Login into SNOC application by Business Admin user 2.Select Administration->Create Organization 3.Enter Organization Name and select Sub-Organization Drop Down as "Dealer" 4.Click on "Continue". 6. Verify whether user is navigated to create organization->Organization Profile . 7. User Povides all information in Organization Profile Screen mentioned below: Organization Name,TinNumber, Registered Mobile Number,ReferenceCode,GSTIN Number,E-Mail,Address Details,Address Type,Address1*,Address2,Country,Province,City,District,Sub-District,Latitude,Longitude,Postal Code and Clicks on "Next" Button 8.Sy | POS(Retailer) organization Template will be created with POS position node.
3 | UC-MS-03 | TC-UC-MS-03-01 | Organization creation - Sales Organization | System Admin user should be already created and active. | 1. Login as Admin user and navigate to Administrator --> Create Organization. 2. User will enter Organization name as "Primary organization" and select the type as Primary Organization and then click 'Next' button. 3. User will provide the Organization Address details and then click 'Next' button. Select Address type as "Organization address". Address details: Address1, Address2, Country Name, Region Name, Sub Region Name, Area Name.4. In "Create Node" tab, Click the 'Add' button and create the Node by providing all the required fields. Transition: Position,Country, Region, Sub Region, AreaTransition values: Sales CCO, Country Name, Region Name, Sub Region Name, Area Name Region Manager, Country Name, Region Name, Sub Region Name, Area Name Area Manager, Country Name, Region Name, Sub Region Name, Area Name4. After Admin confirmation Sales Organization template will be created with Node and Status will be initiated.5. Once Sales Organization is finalized System admin will change the status as Active. | Sales Organization will be created with respective position and nodes.
4 | UC-MS-04 | TC-UC-MS-04-01 | Organization creation - Distributor Organization | System/Sales Admin user should be already created and active. | 1. Login as Admin user and navigate to Administrator --> Create Organization. 2. User will enter Organization name as "Distributor org" and select the type as Distributor and then click 'Next' button. 3. User will fill the Organization profile and Additional information and then click 'Next' button. 4. User will provide the Organization Address details and then click 'Next' button. Select Address type as "Organization address". Address details: Address1, Address2, Country Name, Region Name, Sub Region Name, Area Name. 5. User will provide the Contact information and then click 'Next' button. Fill User Name as 'DIST123' , First Name as 'Dist Admin', Email as 'test@test.org', Mobile Number as '9876543210'. 6. In Organization structure user will select the Organization Name as "Distributor organization" and then click submit button. 7. After Admin confirmation organization will be created and Status will be Active. | Distributor Organization will be created with Organization Admin (User Name - DIST123).
5 | UC-MS-05 | TC-UC-MS-05-01 | Organization creation - POS(Retailer) Organization | Sales Admin/Distributor Admin user should be already created and active. | 1. Login as Admin user and navigate to Administrator --> Create Organization. 2. User will enter Organization name as "POS/Retailer Organization" and select the type as POS and then click 'Next' button. 3. User will fill the Organization profile and Additional information and then click 'Next' button. 4. User will provide the Organization Address details and then click 'Next' button. Select Address type as "Organization address". Address details: Address1, Address2, Country Name, Region Name, Sub Region Name, Area Name. 5. User will provide the Contact information and then click 'Next' button. Fill User Name as 'POS123' , First Name as 'POS Admin', Email as 'test@test.org', Mobile Number as '9876543210'. 6. In Organization Details user will select the Organization Name as "POS Organization" and then click submit button. 7. After Admin confirmation organization will be created and Status should be Active. | POS Organization should be created with Organization Admin (User Name - POS123).
6 | UC-MS-06 | TC-UC-MS-06-01 | User Creation | Organization Admin user should be already created and active. | 1. Login as Admin user and navigate to Administrator --> Create User for specific organization. 2. User can create the user by providing all the required fields. 3. After Organization Admin confirmation user will be created and Status should be initiated. 4. Once user details is finalized Organization admin will change the user status as 'Active' by using "Status Change" icon in right side corner. | Organization user should be created with active status.
7 | UC-MS-07 | TC-UC-MS-07-01 | Create Link between Distribution and POS(Reatiler) Organization | Two Organization Link should be available with Active status | 1. Distribution Organization - Login as Admin user and navigate to My Network --> Sales Network 2. User can Click 'Create' button and fill the date fields and select destination organization value as 'POS Organanization' and destination node and then Link user. 3. After Organization Admin confirmation Link will be created and Status should be initiated. 4. Once Link details is finalized Organization admin will change the Link status as Active by using "Status Change" icon. 5. Finance account should be created for this two organization after link is created. | Link and finance account should be created between Distribution and Retail Organization
8 | UC-MS-08 | TC-UC-MS-08-01 | Master Data Creation - Organizational Unit Master | System Admin user should be already created and active. | 1. In System, Login as Admin user and navigate to Administrator --> Organizational unit. 2. Click the grid view icon for any masters (Eg. Gender, Country, Area,Designation). 3. Click the create button and give the master description value and then click submit button. 4. After admin confirmation master will created with 'initiated' status. 5. Once master value is finalized admin will change the status as Active by using "Status Change" icon. | Organizational unit master should be created with active status.
9 |  | TC-UC-MS-08-02 | Master Data Creation -Generic Master | System Admin user should be already created and active. | 1. In System, Login as Admin user and navigate to Administrator --> Generic Master 2. Click the grid view icon for any masters (Eg. Id Type, Languages). 3. Click create button and give the master description value and then click submit button. 4. After admin confirmation master will created with 'initiated' status. 5. Once master value is finalized admin will change the status as Active by using "Status Change" icon. | Generic master should be created with active status.
10 | UC-MS-09 | TC-UC-MS-09-01 | Role Features - Enable/Disable features by System Admin | System Admin user should be already created and active. | 1. In System, Login as Admin user and navigate to Administrator --> Role Features. 2. Admin User will select the "Assign Features" icon for corresponding role. 3. Admin user can enable/disable the features by using enable the Yes/No option. 4. After enable/ disable the features user will click 'Save' button. 5. After admin confirmation selected features will be available for particular role. | After admin confirmation selected features should be available for particular role.
11 | UC-MS-10 | TC-UC-MS-10-01 | Modify organization - Distributor Organization | Organization Should be there in the system. | 1. In organization, Login as Admin user and navigate to Administrator --> Organization. 2. Click on Edit action icon for particular distributor organization. 3. Modify required fields in Organization profile/Additional information/Organization Address and then click finish button. 4. After confirmation Organization details will be modified. | After confirmation Organization details should be modified.
12 | UC-MS-11 | TC-UC-MS-11-01 | User modification | User should be available with Active/Initiated status. | 1. In organization, Login as Admin user and navigate to Administrator --> Users. 2. Consider the Active/Initiated status user and Click on 'Edit' action icon. 3. Modify required fields for that User and then submit. 4. On confirmation, User details will be modified and status should be the same. | On confirmation, User details should be modified.
13 | UC-MS-12 | TC-UC-MS-12-01 | Assign Transition - Default transition | User should be available with Initiated or Active status. | 1. In organization, Login as Admin user and navigate to Administrator --> Users. 2. Consider the particular user and click on 'Transition' icon. 3. In Default transition click on 'Add' button. 4. Then select the position and click on 'Add' button and then click 'Save' button. 5. After confirmation user will be assigned to selected position. | After confirmation user should be assigned to selected position.
14 | UC-MS-13 | TC-UC-MS-13-01 | Manage User- Unlocking the user | User should be available with Initiated or Active status. | 1. In organization, Login as Admin user and navigate to Administrator --> Users. 2. Consider the particular user and click on 'Manage User' icon. 3. Change the Slider of the "Unlock User" Is Locked ? to "No" 4 Click on "Submit" 5. After Confirmation the user will be able to login to the application | Now the User will be able to login
15 |  | TC-UC-MS-13-02 | Manage User- UnBlocking the user | User should be available with Initiated or Active status. | 1. In organization Login as Admin user and navigate to Administrator --> Users. 2. Consider the particular user and click on 'Manage User' icon. 3. Change the Slider of the "Unblocking" Is BLocked ? to "No" 4 Click on "Submit" 5. After Confirmation the user will be able to login to the application | Now the User will be able to login
16 | UC-MS-14 | TC-UC-MS-14-01 | Manage User- Manage Password | User should be available with Initiated or Active status. | 1. In organization Login as Admin user and navigate to Administrator --> Users. 2. Consider the particular user and click on 'Manage Password' icon. 3. User can change the password by selecting "Change Password" or "Reset Password" option. 4. After providing password details, user will click the submit button. 5. After confirmation password will be changed to particular user. | Now the User will be able to login with updated password
17 | UC-MS-15 | TC-UC-MS-15-01 | Ticker Message creation | Admin/Distributor Admin user should be already created and active. | 1. Login as Admin user and navigate to Ticker Message -> View Ticker Messages. 2. User can create the new ticker message by using 'Create' option. 3. User will provide the ticker message, Start date and corresponding position name. 4. After providing all the required fields user will click the 'submit' button. 5. After confirmation ticker message will be create and will be display in corresponding organization. | After confirmation ticker message will be created and will be displayed in corresponding user screen.
18 |  | TC-UC-MS-15-02 | Ticker Message modification | Ticker Message should be already created and Admin/Distributor Admin user should be already created and active. | 1. Login as Admin user and navigate to Ticker Message -> View Ticker Messages. 2. User can modify ticker message by using 'Edit' option. 3. User will modify required fields and then click on 'submit' button. 4. After confirmation ticker message will be modified and updated message will be display in corresponding user screen. | After confirmation ticker message will be modified and updated message will be displayed in corresponding user screen.
19 | UC-MS-16 | TC-UC-MS-16-01 | Remove User from Node/Position | User should be already created and assigned to any position. | 1. Organization Login as Admin user and navigate to Administrator --> Users. 2. Consider the particular user and click on 'Transition' icon. 3. Admin user can remove the user from position by using "De-associate from position" option. 4. After confirmation user will be removed from corresponding position. | After confirmation user should be removed from corresponding position. | Pass

## Beat
SI.No | Use Case Id | Test Case SI.NO | Test Scenario | Prerequisite | Test Case | Expected Result | Actual Result | Test Case status | Comments
1 | UC-BT-01 | TC-UC-BT-01 -01 | Beat Creation for Sales Representative(FSE) and daily schedular and Mode by Frequncy | The Sales Representative(FSE) should be available and the POS's (Retailers)should be linked to the Distributor Organization | 1. Login as Distributor. 2. Navigate to Beat->"Create Beat" 3. Give all the required fields like "Beat Name","Effective from" and "Effective till" 4. Click on the "Select user" for which user beat going to be created 5. Select the Sales Representative(FSE) 6. Click on the "Select Activities" 7. Select which all the "activities required" for the beat. 8. Click on "Save" 9. Click on the "GO" Button 10. Now Select the "POS" Organization 11. Click on "Next" 12. Now in "Scheduler Screen" 13. Select the Schedular as "Daily" 14. Now Select the Mode as "By Frequency" 15.Now Select the Day as "1" 16. Click on "Finish" 17. Click on "OK" 18. Now we will Get a Message as "Request Processed Successfully" | The Beat Plan should be created with "Initiated" Status with the day Schedule and mode as "By Frequency"
2 | UC-BT-01 | TC-UC-BT-01 -02 | Beat Creation for Sales Representative(FSE) and daily schedular and Mode By Day | The Sales Representative(FSE) should be available and the POS's(Retailers) should be linked to the Distributor Organization | 1. Login as Distributor. 2. Navigate to Beat->"Create Beat" 3. Give all the required fields like "Beat Name","Effective from" and "Effective till" 4. Click on the "Select user" for which user beat going to be created 5. Select the Sales Representative(FSE) 6. Click on the "Select Activities" 7. Select which all the "activities required" for the beat. 8. Click on "Save" 9. Click on the "GO" Button 10. Now Select the "POS" Organization 11. Click on "Next" 12. Now in "Scheduler Screen" 13. Select the Schedular as "Daily" 14. Now Select the Mode as "By Day" 15. Now Click on all the checkbox which all the days are required in a week 16. Click on "Finish" 17. Click on "OK" 18. Now we will Get a Message as "Request Processed Successfully" | The Beat Plan should be created with "Initiated" Status with the Daily Scheduler and mode "by day"
3 | UC-BT-01 | TC-UC-BT-01 -03 | Beat Creation for Sales Representative(FSE) and weekly schedular and mode as "By Weekly" | The Sales Representative(FSE) should be available and the POS's(Retailers) should be linked to the Distributor Organization | 1. Login as Distributor. 2. Navigate to Beat->"Create Beat" 3. Give all the required fields like "Beat Name","Effective from" and "Effective till" 4. Click on the "Select user" for which user beat going to be created 5. Select the Sales Representative(FSE) 6. Click on the "Select Activities" 7. Select which all the "activities required" for the beat. 8. Click on "Save" 9. Click on the "GO" Button 10. Now Select the "POS" Organization 11. Click on "Next" 12. Now in "Scheduler Screen" 13. Select the Schedular as "Weekly" 14. Select all the "check box" like which "day" is required 15. Now Select the Mode as "By Frequency" 16. Now Select the "Weeks" as "1" 17. Click on "Finish" 18. Click on "OK" 19. Now we will Get a Message as "Request Processed Successfully" | The Beat Plan should be created with "Initiated" Status with the "weekly Scheduler" and mode as "By Frequency"
4 | UC-BT-01 | TC-UC-BT-01 -04 | Beat Creation for Sales Representative(FSE) and Monthly schedular and mode as "By week number" | The Sales Representative(FSE) should be available and the POS's(Retailers) should be linked to the Distributor Organization | 1. Login as Distributor. 2. Navigate to Beat->"Create Beat" 3. Give all the required fields like "Beat Name","Effective from" and "Effective till" 4. Click on the "Select user" for which user beat going to be created 5. Select the Sales Representative(FSE) 6. Click on the "Select Activities" 7. Select which all the "activities required" for the beat. 8. Click on "Save" 9. Click on the "GO" Button 10. Now Select the "POS" Organization 11. Click on "Next" 12. Now in "Scheduler Screen" 13. Select the Schedular as "Weekly" 14. Select all the "check box" like which "day" is required 15. Now Select the Mode as "By Week Number" 16.Now Select the "Weeks" as "which week of the month" should be visited 17. Click on "Finish" 18. Click on "OK" 19. Now we will Get a Message as "Request Processed Successfully" | The Beat Plan should be created with "Initiated" Status with the "weekly Scheduler" and mode as "By Week Number"
5 | UC-BT-01 | TC-UC-BT-01 -05 | Beat Creation for Sales Representative(FSE) and weekly schedular and mode as "By week number" | The Sales Representative(FSE) should be available and the POS's(Retailers) should be linked to the Distributor Organization | 1. Login as Distributor. 2. Navigate to Beat->"Create Beat" 3. Give all the required fields like "Beat Name","Effective from" and "Effective till" 4. Click on the "Select user" for which user beat going to be created 5. Select the Sales Representative(FSE) 6. Click on the "Select Activities" 7. Select which all the "activities required" for the beat. 8. Click on "Save" 9. Click on the "GO" Button 10. Now Select the "POS" Organization 11. Click on "Next" 12. Now in "Scheduler Screen" 13. Select the Schedular as "Weekly" 14. Select all the "check box" like which "day" is required 15. Now Select the Mode as "By Week Number" 16.Now Select the "Weeks" as "which week of the month" should be visited 17. Click on "Finish" 18. Click on "OK" 19. Now we will Get a Message as "Request Processed Successfully" | The Beat Plan should be created with "Initiated" Status with the "weekly Scheduler" and mode as "By Week Number"
6 | UC-BT-01 | TC-UC-BT-01 -06 | Beat Creation for Sales Representative(FSE) and Monthly schedular and by date | The Sales Representative(FSE) should be available and the POS's(Retailers) should be linked to the Distributor Organization | 1. Login as Distributor. 2. Navigate to Beat->"Create Beat" 3. Give all the required fields like "Beat Name","Effective from" and "Effective till" 4. Click on the "Select user" for which user beat going to be created 5. Select the Sales Representative(FSE) 6. Click on the "Select Activities" 7. Select which all the "activities required" for the beat. 8. Click on "Save" 9. Click on the "GO" Button 10. Now Select the "POS" Organization 11. Click on "Next" 12. Now in "Scheduler Screen" 13. Select the Schedular as "Monthly" 14. Now Select the Mode as "By Date" 15.Now Select the Dates Which is required 16. Now Select the "Mode" as "By Frequncy" 17. Click on "Finish" 18. Click on "OK" 19. Now we will Get a Message as "Request Processed Successfully" | The Beat Plan should be created with "Initiated" Status with the "Monthly Scheduler" and mode as "By Frequency"
7 | UC-BT-01 | TC-UC-BT-01 -07 | Beat Creation for Sales Representative(FSE) and Monthly schedular by date and by month | The Sales Representative(FSE) should be available and the POS's(Retailers) should be linked to the Distributor Organization | 1. Login as Distributor. 2. Navigate to Beat->"Create Beat" 3. Give all the required fields like "Beat Name","Effective from" and "Effective till" 4. Click on the "Select user" for which user beat going to be created 5. Select the Sales Representative(FSE) 6. Click on the "Select Activities" 7. Select which all the "activities required" for the beat. 8. Click on "Save" 9. Click on the "GO" Button 10. Now Select the "POS" Organization 11. Click on "Next" 12. Now in "Scheduler Screen" 13. Select the Schedular as "Monthly" 14. Now Select the Mode as "By Date" 15.Now Select the Dates Which is required 16. Now Select the "Mode" as "By Month" 17. Click on "Finish" 18. Click on "OK" 19. Now we will Get a Message as "Request Processed Successfully" | The Beat Plan should be created with "Initiated" Status with the "Monthly Scheduler" and mode as "By Frequency"
8 | UC-BT-01 | TC-UC-BT-01 -08 | Beat Creation for Sales Representative(FSE) and Monthly schedular and by day and frequency | The Sales Representative(FSE) should be available and the POS's(Retailers) should be linked to the Distributor Organization | 1. Login as Distributor. 2. Navigate to Beat->"Create Beat" 3. Give all the required fields like "Beat Name","Effective from" and "Effective till" 4. Click on the "Select user" for which user beat going to be created 5. Select the Sales Representative(FSE) 6. Click on the "Select Activities" 7. Select which all the "activities required" for the beat. 8. Click on "Save" 9. Click on the "GO" Button 10. Now Select the "POS" Organization 11. Click on "Next" 12. Now in "Scheduler Screen" 13. Select the Schedular as "Monthly" 14. Now Select the Mode as "By Day" 15.Now Select the Dates Which is required 16. Now Select the "Mode" as "By Frequncy" 17. Click on "Finish" 18. Click on "OK" 19. Now we will Get a Message as "Request Processed Successfully" | The Beat Plan should be created with "Initiated" Status with the "Monthly Scheduler" and mode as "By Frequency"
9 | Uc-BT-01 | TC-UC-BT-01 -09 | Beat Creation for Sales Representative(FSE) and Yearly schedular | The Sales Representative(FSE) should be available and the POS's(Retailers) should be linked to the Distributor Organization | 1. Login as Distributor. 2. Navigate to Beat->"Create Beat" 3. Give all the required fields like "Beat Name","Effective from" and "Effective till" 4. Click on the "Select user" for which user beat going to be created 5. Select the Sales Representative(FSE) 6. Click on the "Select Activities" 7. Select which all the "activities required" for the beat. 8. Click on "Save" 9. Click on the "GO" Button 10. Now Select the "POS" Organization 11. Click on "Next" 12. Now in "Scheduler Screen" 13. Select the Schedular as "Yearly" 14. Now Select the Mode as "in between 10" 15.Now Select the Month which is required "" 16. Now choose the date which is required 17. Click on "Finish" 18. Click on "OK" 19. Now we will Get a Message as "Request Processed Successfully" | The Beat Plan should be created with "Initiated" Status with the "Monthly Scheduler" and mode as "By Frequency"
10 | UC-BT-02 | UC-BT-02-01 | Changing the status of the Beat | The Beat should be Created and it will be in "Initiated" Status | 1. Login as Distributor 2. Navigate to "Beat" -> Beats 3. Click on the "Change Status" Icon Under "Actions" Button 4. Select the "Active" status from the Drop down list 5. Click on "Submit" 6. Click on "OK" 7. Now we will get the message like "Request Processed Successfully" | The Beat Plan "status" has been changed to "Active"
11 | UC-BT-03 | UC-BT-03 -01 | View the Beat Created | The Beat should be Created and it will be in "Active " Status | 1. Login as Distributor 2. Navigate to "Beat" -> "Beats" 3. Select the Particular Beat 4. Click on the "view" Button under the "Action" Items 5. We can view all the Details like "Beat Name " , "Organization", "Effective From " and "Effective Till" date", "Selected Node" , "Activities" , "Organizations" 6. Click on "Next" 7. In Schedular Screen can be able to view the schedular | Should be able to view the "Beat Plan"
12 | UC-BT-03 | UC-BT-03 -01 | Edit the Beat Created | The Beat should be Created and it will be in "Active " Status | 1. Login as Distributor 2. Navigate to "Beat" -> "Beats" 3. Select the "Particular Beat" 4. Click on the "Edit" Button under the "Action" Items 5. We can Edit all the Details like "Beat Name " , "Organization", "Effective From " and "Effective Till" date", "Selected Node" , "Activities" , "Organizations" 6. Click on "Next" 7. In Schedular Screen can be able to edit the schedular for the Beat | Should be able to edit the Beat Plan
13 | UC-BT-04 | UC-BT-04 -01 | Beat DashBoard- Summary | The Beat should be Created and it will be in "Active " Status | 1. Login as Distributor 2. Navigate to "Beat" -> "Beats" 3. Select the "Particular Beat" 4. Click on the "Beat Dashboard" Button under the "Action" Items 5, Click on the "Summary" 6. Able to View the "Beat Name" 7. Able to view the "Beat Date" 8. Able to view the "Position" 9. Able to view the "Total Organizations" 10. Able to view the "Unplanned Organiations" 11. Able to view the "Users" | Should be able to view the "summary" of the Beat Plan under the Beat Dashboard
14 | UC-BT-04 | UC-BT-04 -02 | Beat DashBoard- Map View | The Beat should be Created and it will be in "Active " Status | 1. Login as Distributor 2. Navigate to "Beat" -> "Beats" 3. Select the "Particular Beat" 4. Click on the "Beat Dashboard" Button under the "Action" Items 5, Click on the "Map View" 6. Able to View the "Planned Route" in a map 7. Able to view the "Actual Route he visited" in a map 8. Able to view the "Organizations with Sales" in a map 9. Able to view the "Captured Location" in a map 10. Able to view the "Organizations without sales" in a map 11. Able to view the "To Be Visited" in a map 12. Able to view the "Track Line" in a map 13. Able to view the "Track Point" in a map 14. Able to view the "Unplanned Beat" in a map | Should be able to view the "Map view" of the Beat Plan under the Beat Dashboard
15 | UC-BT-04 | UC-BT-04 -03 | Beat DashBoard-Grid view | The Beat should be Created and it will be in "Active " Status | 1. Login as Distributor 2. Navigate to "Beat" -> "Beats" 3. Select the "Particular Beat" 4. Click on the "Beat Dashboard" Button under the "Action" Items 5, Click on the "Grid view" 6. Able to view all the activities assigned 7. Select the "Execute" Button on a particular activity 8. Able to view the Details of the Activities performed with date and time | Should be able to view the "ACtivities" Performed and when and what has been performed of the Beat Plan under the Beat Dashboard
16 | UC-BT-05 | UC-BT-05-01 | Creation of the "Self Beat" | The Sales Representative(FSE) Should be Created and assigned to any organiation and it should be "Active" Status | 1. Login as Sales Representative(FSE) 2. Navigate to "Beat" -> "Create Self Beat" 3. Give the "Beat Name","Effective From" , "Effective Till ", "Select Activities", 4. Select the "Organizations" 5. Click on "Next" 6. Now select the scheduler when it has to be performed 7. Click on "FInish" 8. Click on "OK" 9. Now the Message will be displayed like "Request Processed Successfully" 10. Now the Beat will be created with "Initiated " Status | Should be able to create the self beat and Status will be "Initiated Status"
17 | UC-BT-07 | UC-BT-07-01 | Re-assigning the Beat to another Sales Representative(FSE) | The Beat should be Created and it should be in "Active" Status and it should be assigned to one Sales Representative(FSE) | 1. Login as Distributor 2. Navigate to Beat -> "Assigned" 3. Select the "Beat Name" from "Drop Down" 4. Select the "Beat Plan" from Drop Down" (Beat Plan will be Displayed with effective from and Effective till " In a Beat Plan 5. "Effective from" date will be displayed according to the Beat Plan selected 6. "Effective till" date will be displayed according to the Beat Plan selected 7. Click on "Fetch" 8. The Beat which is available will be displayed 9. Click on "Beat Plan " available 10. Click on "Re-assign" 11. Now the hirarchy of that organization will be displayed 12. Now select the Sales Representative(FSE) to whom it has to be assigned 13. Now select the "user" by Clicking on the "check box" under "Actions" 14. Now Click on "Select" 15. Now it will be assigned to the other user 16. Now Click on "Submit" 17. Now Click on "OK" 18. Now the message will be displayed as "Request Processed Successfully" | The Beat SHould be "De-associated"with the existing Sales Representative(FSE) and should be assigned to new Sales Representative(FSE)
18 | UC-BT-07 | UC-BT-07-01 | Reports of the Beat- Beat Plan Summary Report | The Beat has to be Created and the Transactions has to be performed | 1. Login as Distributor 2. Navigate to "Beat" -> " Reports" 3. Select the "Beat Plan Summary Reports" 4. Give the Details like "From Date", "To Date", 5. Select on "Report Type" as "PDF" or "EXCEL" Format 6. Click on "Submit" 7. The Report will be downloaded with details like "Partner Id", "Beat Plan Name","Beat Name", "Scheduled On","No of Outlets","Assigned to","POS Id","POS Name","Address of the Pos","Status" | The Report should be Downloaded with the following details "Partner Id", "Beat Plan Name","Beat Name", "Scheduled On","No of Outlets","Assigned to","POS Id","POS Name","Address of the Pos","Status"
19 | UC-BT-07 | UC-BT-07-04 | Reports of the Beat- "Outlets Visisting Frequency" | The Beat should Be Created and the transactions has to be performed | 1. Login as Distributor 2. Navigate to "Beat" -> " Reports" 3. Select the "Outlets Visiting Frequency" 4. Select the "Position" 5. Select the "User" 5. Select on "Report Type" as "PDF" or "EXCEL" Format 6. Select the "End date" 6. Click on "Submit" 7. The Report will be downloaded with details like "Retailer name", "Visiting Frequency" | The Report should be Downloaded with the following details "Retailer name", "Visiting Frequency"
20 | UC-BT-07 | UC-BT-07-05 | Reports of the Beat- "In - Out Report" | The Beat should Be Created and the transactions has to be performed | 1. Login as Distributor 2. Navigate to "Beat" -> " Reports" 3. Select the "In-Out Report" 4. Select the "Position" 5. Select the "User" 5. Select on "Report Type" as "PDF" or "EXCEL" Format 6. Select the "End date" 6. Click on "Submit" 7. The Report will be downloaded with details like "Partner Id", "Beat Plan Name","Beat Name", "Scheduled On","No of Outlets","Assigned to","POS Id","POS Name","Address of the Pos","Status" | The Report should be Downloaded with the following details "Partner Id", "Beat Plan Name","Beat Name", "Scheduled On","No of Outlets","Assigned to","POS Id","POS Name","Address of the Pos","Status"

## MobileApp
SI.No | Use Case Id | Test Case SI.NO | Test Scenario | Prerequisite | Test Case | Expected Result | Actual Result | Test Case status | Comments
1 | UC-MOB-01 | TC-UC-01-01 | Sync Menu – When the user logins into the application needs to sync first before performing the transactions | The Sales Representative(FSE) has to be Created | 1. Login as Sales Representative(FSE) using mobile app 2. Navigate to "Sync" menu 3. click on " Download all" Option to download all like "Maters","Stock", and "Beat" 4. After downloading has been finished which all have been downloaded the right tick will be marked and if not downloaded it will be marked as Wrong mark | All the stock masters will be downloaded
2 | UC-MOB-02 | TC-UC-MOB-02-01 | Secondary Sales to the unplanned POS(Retailer) | The Organization has to be linked and Hirarchy has to be maintained and stock , masters should be downloaded from sync menu | 1. Login as Sales Representative(FSE) into the mobileapp 2. Navigate to "Hierarchy" 3. Select the "Organization" 4. Click on the "Secondary Sales" 5. Give the "Serial Number" 6. CLick on the "Plus" button 7. The Product will be displayed 8. Click on "Proceed" 9. All the Product Information will be displayed like Click on "Submit" 10. The Reciept will be displayed | The Order has to be placed and the stock should be moved to POS(Retailer) inventory account
3 | UC-MOB-02 | TC-UC-MOB-02-02 | Capturing the Geo location of the unplanned POS(Retailer) | The Organization has to be linked and Hirarchy has to be maintained and the masters should be downloaded from sync menu | 1. Login as Sales Representative(FSE) into the mobileapp 2. Navigate to "Hierarchy" 3. Select the "Organization" 4. Click on the "Capture POS(Retailer) Lat/long" 5. Click on "Get Location" 6. If the lat/long is not able to capture "we will get the pop-up like" "NO GPS GPS SIgnal Not available. Do you want to capture from Network?", 7. Click on "Yes" 8. The Network lat/Long will be captured 9 click on "Save" 10. The Location will be Saved | The Geo Location should be captured
4 | UC-MOB-02 | TC-UC-MOB-02-03 | To View the Credit limit of the POS(Retailer) | The Credit Limit of the POS(Retailer) should have been set and stock and masters menu should be downloaded from sync menu | 1. Login as Sales Representative(FSE) into the mobileapp 2. Navigate to "Hierarchy" 3. Select the "Organization" 4. Click on the "View Credit Limit" 5. The "Available Credit limit" will be shown for that particular organization | The POS(Retailer) should be able to check the available credit limit if the credit limit is not set by default it will be 9999999.99
5 | UC-MOB-02 | TC-UC-MOB-02-04 | To perform the Survey | ThePOS(Retailer) organization should contain the lat long . The stock and the masters menu should be downloaded from the sync menu | 1. Login as Sales Representative(FSE) into the mobileapp 2. Navigate to "Hierarchy" 3. Select the "Organization" 4. Click on the "Survey" 5. ALl the survey forms will be displayed 6. Fill all the required fields in the survey 7. Click on "Submit" | Should be able to perform the survey
6 | UC-MOB-02 | TC-UC-MOB-02-05 | To View the Survey | The POS(Retailer) organization should contain the lat long . The stock and the masters menu should be downloaded from the sync menu | 1. Login as Sales Representative(FSE) into the mobileapp 2. Navigate to "Hierarchy" -> “Transactions” 3. All the Transactions will be displayed 4. Select the “Transactions” 5. All the Details will be displayed | Should be able to perform the survey
7 | UC-MOB-02 | TC-UC-MOB-02-06 | Capture POS(Retailer) Image of unplanned POS(Retailer) | The POS(Retailer) organization should contain the lat long. The stock and the masters menu should be downloaded from the sync menu | 1. Login as Sales Representative(FSE) into the mobileapp 2. Navigate to "Hierarchy" 3. Select the "Organization" 4. Click on the "Capture POS(Retailer) image" 5. Select the "Image size" like " Large(1024*768)" or "Medium (640*480)" 6. CLick on "add" 7. The Phone Camera wll be Opened and capture the Image 8. After Capturing The image will be displayed 9. Click on "Save" | The Sales Representative(FSE) should be able to capture the POS(Retailer) image and the image should be uploaded from sync->Upload Menu and the image can be viewed in organization
8 | UC-MOB-03 | UC-MOB-03-01 | To Sales Representative(FSE) the Stock Adjustment | The Stock and masters should be downloaded from the sync menu The Sales Representative(FSE) should contain the stock . | 1. Login as "Sales Representative(FSE)" in Mobileapp 2. Navigate to "My Profile" 3. Click on "Stock Adjustment" 4. Give the "Serial Number" 5. Click on the "Plus" Button 6. Click on "Next" 7. Select the "Reason" as "Damaged" or "Lost/Stolen" 8. Give the "Comments" 9. Click on "Proceed" 10. After CLicking on Proceed we will get the "Pop-up" like "Activities" ,"Are you Sure" 11. Click on "Yes" 12. The Order will be placed | The POS(Retailer) Organization should be able to give back the damaged/Lost Stock and the Order will be placed
9 | UC-MOB-03 | TC-UC-MOB-03-02 | Viewing the Profile of Sales Representative(FSE) | The "Sales Representative(FSE)" should be available and the Masters should be downloaded from the sync menu | 1. Login as "Sales Representative(FSE)" in Mobileapp 2. Navigate to "My Profile" 3. Click on "View Profile" 4. CLick on "Contact" 5. Select the "Primary" 6. It Displays all the Information l 6. CLick on "Address" 7. Select the "Organization Addess" 8. It Displays the information 9. while Clicking on "Roles" current role of the logged in user will be displayed | The "Sales Representative(FSE)" should be able to view his profile information
10 | UC-MOB-04 | TC-UC-MOB-04-01 | Beat Plan- Secondary Sales | The Beat should be created and it should be in "Active" Status and the Beat and stock should be downloaded from the sync menu | 1. Login as Sales Representative(FSE) into the mobileapp 2. Navigate to "Beat Plan" 3. List of "POS's(Retailers)," will be Displayed which was assigned while creating a "Beat Plan" 4. Click on "Edit" Button to Perform the Trasantions 5.4. Click on the "Secondary Sales" 5. Give the "Serial Number" 6. CLick on the "Plus" button 7. The Product will be displayed 8. Click on "Proceed" 9. All the Information will be displayed like " 10. Click on "Submit" 11 The Reciept will be displayed | The FSE Should be able to do the secondary sales through beat for the POS(Retailer)
11 | UC-MOB-04 | TC-UC-MOB-04-02 | Beat Plan lat/long- Capture The geo locationPOS(Retailer) | The Beat should be created and it should be in "Active" Status and the Beat and stock should be downloaded from the sync menu | 1. Login as Sales Representative(FSE) into the mobileapp 2. Navigate to "Beat Plan" 3. List of "POS's(Retailers)" will be Displayed which was assigned while creating a "Beat Plan" 4. Click on "Edit" Button to Perform the Trasantions | The FSE Should be able to do the capture the lat/long of POS(Retailer)) organization
12 | UC-MOB-04 | TC-UC-MOB-04-03 | Beat Plan - Capture POS(Retailer) Image | The Beat should be created and it should be in "Active" Status and the Beat and stock should be downloaded from the sync menu | 1. Login as Sales Representative(FSE) into the mobileapp 2. Navigate to "Beat Plan" 3. List of "POS'sRetailers)" will be Displayed which was assigned while creating a "Beat Plan" 4. Click on "Edit" Button to Perform the Trasantions 5. Click on the "Capture POS(Retailer)) Lat/long" 6. Click on "Get Location" 7. If the lat/long is not able to capture "we will get the pop-up like" "NO GPS GPS SIgnal Not available. Do you want to Capture from Network?", 8. Click on "Yes" 9. The Network lat/Long will be captured 10 click on "Save" 11. The Location will be Saved" | The Sales Representative(FSE) Should be able to do the capture the POS(Retailer) image for the particular organization through beat and the image can be viewed in the beat dashboard
13 | UC-MOB-04 | TC-UC-MOB-04-04 | Beat Plan - Survey | The Beat should be created and it should be in "Active" Status and the Beat and stock should be downloaded from the sync menu. The survey form should be created by the Admin | 1. Login as Sales Representative(FSE) into the mobileapp 2. Navigate to "Beat Plan" 3. List of "POS's(Retailers)" will be Displayed which was assigned while creating a "Beat Plan" 4. Click on "Edit" Button to Perform the Trasantions 5.4. Click on the "Survey" 5. Give the "Serial Number" 6. Give all the Required Fields 7. Click on "Submit" | The Sales Representative(FSE) should be able to perform the survey
14 | UC-MOB-06 | TC-UC-MOB-06-01 | Tertiary Sales – To sell the products directly to customers | Tertiary Sales All the masters and stock should be downloaded from the sync menu | 1. Login as Sales Representative(FSE) into the mobileapp 2. Navigate to Tertiary Sales menu 3. Give the Serial Number in the "Start Range" 4. Click on "Plus" Button 5. The Product will be didplayed 6. Click on "Next" 7. In Summary Screen The details will be displayed 8. Click on "Submit" 9. The Pop up will displayed with a message "Activities" "Are you Sure ?" 10. Click on "Yes" 11. The Reciept wil be displayed with the Details | The Sales Representative(FSE) should be able to perform the tertiary sales to customers
15 | UC-MOB-11 | TC-UC-MOB-11-01 | Secondary Sales Price Guidance | The Criteria should have been set , and the stock and masters should have been downloaded from the sync menyu | 1. Login as the Sales Representative(FSE) from the mobile app 2. Navigate to Hirarchy -> Select the particular organization 3. Select the "Secondary Sales" 4. Give the Serial Number in "Select Range" 5. All the "Products" , "qty * Amt" , " Discount " will be displayed 6. The Amount which is displayed is "The Price of the Secondary Sales will be displayed" | The Price will be displayed when doing the sale
16 | UC-MOB-12 | TC-UC-MOB-12-01 | Serial Number Search | Serial Number Search the stock should be downloaded from the sync menu | 1. Login as the Sales Representative(FSE) from the mobile app 2. Navigate to Hirarchy -> Select the particular organization 3. Select the "Secondary Sales" 4. Give the Serial Number in "Select Range" 5. All the "Products" , Which has the same serial number That products will be displayed with the "Price per unit" and "quantity" | The FSE should be able search the serial no while doing the sale

## Product
SI.No | Use Case Id | Test Case SI.NO | Test Scenario | Prerequisite | Test Case | Expected Result | Actual Result | Test Case status | Comments
1 | UC-PR-01 | TC-UC-PR-01-1 | Product Line Creation | Sales Admin user should be already created and active. | 1. Sales Admin user after login will select Product -> Master. 2. Click the Grid view icon for Product Line. 3. Click create button and give Value Description value as 'Mobility' and then submit. 4. After Admin confirmation Product Line will be created and Status should be initiated. 5. Once Product Line is finalized user will change the status as Active. | Product Line should be created with Active status.
2 | UC-PR-01 | TC-UC-PR-01-2 | Product Categories Creation | Product line should be already created and active. | 1. Admin user after login will select Product --> Master. 2. Click the Grid view icon for Product Categories. 3. Click create button and give the description value as 'RCV'. 4. In "Linked Fields" option select Product master dropdown as 'Product Line' & Product value dropdown as 'Mobility' and then submit. 5. After Admin confirmation Product Categories will be created and Status should be initiated. 6. Once Product Categories is finalized user will change the status as Active. | Product Categories should be created with Active status.
3 | UC-PR-01 | TC-UC-PR-01-3 | Product Sub Categories Creation | Product line and Product Categories should be already created and active. | 1. Admin user after login will select Product --> Master. 2. Click the Grid view icon for Product Sub Categories. 3. Click create button and give Value Description value as 'RCV'. 4. In "Linked Fields" option select Product master dropdown as 'Product Categories' & Product value dropdown as 'RCV' and then submit. 5. After Admin confirmation Product Sub Categories will be created and Status should be initiated. 6. Once Product Sub Categories is finalized user will change the status as Active. | Product Sub Categories should be created with Active status.
4 | UC-PR-02 | TC-UCSOPR-02-1 | Product Creation | Product Categories should be already created. | 1. Admin user after login will select Product --> Create Product. 2. Give name as 'RCV10' and fill the Ext. Product Id, Effective from, Effective Till and other required fields. 3. Select Product Categories as 'RCV' and Product Sub Categories as 'RCV' and select the value in 'Is Serialized' dropdown. i. If serialized product is needed then select value as 'Yes', otherwise select value as 'No'. ii. If product is serialized then select the serial type as 'Number' or 'Character'. 4. After provide all the required fields click the submit button. 5. After Admin confirmation Product will be created and Status should be initiated. 6. Once Product is finalized user will change the status as Active. | Product should be created with Active status.
5 | UC-PR-03 | TC-UCSOPR-03-1 | Product Modification | Product should be already created and status should be active. | 1. Admin user after login will select Product --> View Product. 2. User can set or modify the product price, base price, minimum order, maximum order and multiplication factor values in Product property section by using 'Edit' option. 3. After modified some fields admin user will click the submit button. 4. After confirmation product details will be modified and status should be active. | After confirmation product details should be modified and status should be active.
6 | UC-PR-03 | TC-UCSOPR-03-2 | Set Criteria to product | Product should be already created. | 1. Admin user after login will select Product --> View Product. 2. In Criteria section, Admin user can create new criteria by clicking 'Add' button. 3. User will Set Criteria price and select start date & end date and will enable 'Is criteria' option. 4. Select the criteria by click (...) option. User will select 'Field' and 'Value' based on needed and user will click the 'Select' button. 5. Then user confirm the Criteria and After confirmation Criteria will be added for particular product. | After user confirmation Criteria should be created for particular product.

## Stock & Sales Management
SI.No | Use Case Id | Test Case SI.NO | Test Scenario | Prerequisite | Test Case | Expected Result | Actual Result | Test Case status | Comments
1 | UC-SM-01 | TC-UC-SM-01-01 | Order Creation - Stock Entry | Products should be available on Organization. | 1. login into application with specific user.select Stock --> Stock Entry. 2. Select the product name for which is need to do stock entry. i. If product is non-serialized, enter the product quantity and then select supplier account(If need). ii. If product is Serialized (Numeric Type), Enter the start and end serial numbers and then select supplier account(If need). iii. If product is Serialized (Character/Alpha numeric Type), Enter the one or more character type serial numbers for product and then select supplier account(If need). 3. After giving product details, click on submit button. 4. After confirmation stock details will be added in Inventory accounts. | After confirmation stock details should be added in Inventory accounts.
2 | UC-SM-02 | TC-UC-SM-02-01 | Order Creation - Stock Transfer | Products and Stock should be available on Organization. | 1. Login into application with specific user.select Stock --> Stock Transfer. 2. Select To inventory account and product name for which is need to do stock transfer. i. If product is non-serialized, enter the product quantity. ii. If product is Serialized (Numeric Type), Enter the start and end serial numbers. iii . If product is Serialized (Character/Alpha numeric Type), Enter the one or more character type serial numbers for product. 3. After giving product details, click on submit button. 4. After confirmation stock details will be update in both from and To inventory accounts. | After confirmation stock details should be update in both from and To inventory accounts.
3 | UC-SM-03 | TC-UC-SM-03-01 | View Stock | Stock should be available to view own stock and to view child stock , hierarchy should have their stock. | 1. Login into application with specific user Stock --> Inventory Accounts. 2. In My Accounts tab user will click on "Inventory Details" icon to view own stock. 3. In Organization Accounts tab user will click on "Inventory Details" icon to view child/Organization users stock. 4. For serialized product, User can Check the status of serial numbers by using "View Serial" option.
4 | UC-SM-04 | TC-UC-SM-04-01 | Order Creation - Stock Return | Stock transfer should be already done | 1. Login into application with specific use.Select Stock --> Stock return. 2. Select the Return From & return To inventory accounts and product name for which is need to do Stock return. i. If product is non-serialized, enter the product quantity. ii. If product is Serialized (Numeric Type), Enter the start and end serial numbers. iii . If product is Serialized (Character/Alpha numeric Type), Enter the one or more character type serial numbers for product. 3. Give reason and then click on submit button. 4. After confirmation stock details will be update in both from and To inventory accounts. | After confirmation stock details will be update in both from and To inventory accounts.
5 | UC-SM-05 | TC-UC-SM-05-01 | Order Creation - Stock Adjustment | Products and Stock should be available on Organization. | 1. Organization user after login will select Stock --> Stock Adjustment. 2. User will select the adjustment type and then Select the inventory account and product name for which is need to do stock Adjustment. i. If product is non-serialized, enter the product quantity. ii. If product is Serialized (Numeric Type), Enter the start and end serial numbers. iii . If product is Serialized (Character/Alpha numeric Type), Enter the one or more character type serial numbers for product. 3. Give reason and then click on submit button. 4. After confirmation stock will be adjust from inventory account. | After confirmation stock should be adjust from inventory account.
6 | UC-SM-06 | TC-UC-SM-06-01 | Order Creation - Direct Sale/ Secondary sale | Products and Stock should be available on Organization. | 1. Organization user after login will select Sales --> Secondary sales. 2. Select the TO inventory account and product name for which is need to be sale. i. If product is non-serialized, enter the product quantity. ii. If product is Serialized (Numeric Type), Enter the start and end serial numbers. iii . If product is Serialized (Character/Alpha numeric Type), Enter the one or more character type serial numbers for product. 3. Select the payment mode and then click on submit button. 4. After confirmation sale should be done and stock will be update in buyer and seller inventory accounts. | After confirmation sale should be done and stock should be update in buyer and seller inventory accounts.
7 | UC-SM-07 | TC-UC-SM-07-01 | Order Creation - Tertiary Sale | Products and Stock should be available on Organization. | 1. Login into application with specific user select Sales --> Tertiary Sale. 2. Enter the product name for which is need to be sale. i. If product is non-serialized, enter the product quantity. ii. If product is Serialized (Numeric Type), Enter the start and end serial numbers. iii . If product is Serialized (Character/Alpha numeric Type), Enter the one or more character type serial numbers for product. 3. Select the payment mode and then click on submit button. 4. After confirmation sale should be done and stock will be update in seller inventory accounts. | After confirmation sale should be done and stock will be update in seller inventory accounts.
8 | UC-SM-08 | TC-UC-SM-08-01 | Order Creation - Sale Return | Sale should be already done | 1. Organization user after login will select Sales --> Sale return. 2. Select the Return From & return To inventory accounts and product name for which is need to do Sale return. i. If product is non-serialized, enter the product quantity. ii. If product is Serialized (Numeric Type), Enter the start and end serial numbers. iii . If product is Serialized (Character/Alpha numeric Type), Enter the one or more character type serial numbers for product. 3. Give reason and then click on submit button. 4. After confirmation stock details will be update in both from and To inventory accounts. | After confirmation stock details will be update in both from and To inventory accounts.

## Target Management
SI.No | Use Case Id | Test Case SI.NO | Test Scenario | Prerequisite | Test Case | Expected Result | Actual Result | Test Case status | Comments
1 | UC-TG-01 | TC-UC-TG-01 | Add metrics for Distribution hierarchy | The template for the distributor hierarchy should be created | 1.Login into SNOC application by specific user 2.Select target->target master 3.List of all target names will be displayed. 4.Click on view metrics action button. 5.Click on add metrics. 6. Select the start date. 7.Select the required sale amount based on category. 8.click on submit. | 1.User should be able to perform each step in the process of adding metrics 2.User should be able to click view metrics action button. 3. User should be able to add metrics. 4. User should be able to select the start date 5. User should be able to select the required sale amount based on category.
2 | UC-TG-02 | TC-UC-TG-02 | Edit metrics for Distribution hierarchy | Metrics should have been created | 1.Login into SNOC application by specific user 2.Select target->target master. 3.List of all target names will be displayed. 4.click on view metrics action button. 5.Displays the list of metrics created. 6.Click on edit action button. 7.Modify the required sale amount based category. 8.Click on submit | 1.User should be able to perform each step in the process of edit metrics 2. User should be able to modify the required sale amount based category.
3 | UC-TG-03 | TC-UC-TG-03 | View target metrics for Distribution hierarchy | Metrics should have been created | 1.Login into SNOC application by specific user 2.Select target->target master. 3.List of all target names will be displayed. 4.click on view metrics action button. 5.Displays the list of metrics created. 6.Click on view target metrics tree to view the metrics tree details. | 1.User should be able to perform each step in the process of view metrics 2. User should be able to Click on view target metrics tree to view the metrics details
4 | UC-TG-04 | TC-UC-TG-04 | Revise formula for Distribution hierarchy | 1.Target for Distributor should be pre-configured 2. Target metrics should be created. | 1.Login into SNOC application by specific user 2.Select target->target master. 3.List of all target names will be displayed. 4.click on view formula action button. 5.Click on Revise Formula. 6.Select the Start date. 7.Enter the Number of cycles. 8.Select Aggregation on (sales/target). 10.Enter the cycle weightage. 11.Click on submit. | 1. User should be able to Revise Formula. 2. User should be able to Select the Start date. 3 .User should be able to enter the Number of cycles. 4. User should be able to Select Aggregation on (sales/target). 6. User should be able to enter the cycle weightage
5 | UC-TG-04 | TC-UC-TG-05 | Edit formula for Distribution hierarchy | Formula should have been created | 1.Login into SNOC application by specific user 2.Select target->target master. 3.List of all target names will be displayed. 4.click on view formula action button. 5.Displays the list of formulae created. 6.Click on edit formula button to modify the target formula details for the selected start date. 7.Click on submit | 1.User should be able to edit formula. 2.User should be able to modify the target formula details for the selected start date.
6 | UC-TG-06 | TC-UC-TG-06 | Set target for Distribution hierarchy | 1.Metrics and formula should exist for a target period | 1.Login into SNOC application by specific user 2.Select target->Set target 3.Select the target name and target period. 4.Select the target assignee 5.Enter the target for the metrics. 6.Click on submit. | 1.User should be able to select the target name and target period. 2. User should be able to select the target assignee. 3. User should be to enter the new target.
7 | UC-TG-07 | TC-UC-TG-07 | Modify target for Distribution hierarchy by parent node to his child node | 1.Metrics and formula should exist for a target period | 1.Login into SNOC application by specific user 2.Select target-> Modify target 3.Select the target name and target period. 4.Select the target assignee 5.Enter the target for the metrics. 6.Click on submit. | 1.User should be able to select the target name and target period. 2. User should be able to select the target assignee. 3. User should be to enter the new target.
8 | UC-TG-08 | TC-UC-TG-08 | View Target for Distribution hierarchy | 1.Target should be set for the corresponding user | 1.Login into SNOC application by specific user 2.Select target->View target 3.Select the target name and target period to view the targe | 1. User should be able to select the target name and target period to view the target.
9 | UC-TG-09 | TC-UC-TG-09 | View achievements for secondary Sale by performed by distributor | 1. Target should be set and Secondary sales should be performed. | 1. Login into SNOC application by specific user 2. Select target->view target 3. Enter target name and target period. 4.After Secondary sales are performed and Order is placed, achieved target and achieved percentage will be calculated. | 1. User should be able select the target name and target period to view the achievements on DC acknowledgment